## Project Overview
YOLO11 Integrated AI Inspection & Retraining System
Project Overview ? Formal Software Baseline v1.0.0
Item | Value | Notes
Project | YOLO11 Integrated AI Inspection & Retraining System | Workspace containing separate inference and training repositories.
Purpose | PCBA / component AOI inspection with controlled operator review and retraining | YOLO for known components; Anomalib and traditional CV for complementary checks.
Owner | Dio Wang | Application, integration, and release-document owner.
Current Version | v1.0.0 | First formal software baseline; Git tag and release package are still pending.
Formal Release Date | 2026-08-05 | Software release date, not production-line acceptance date.
Development Period | 2025/12 ? 2026/08 | Integrated product timeline represented by this revision note.
Language | Python 3.10?3.11 | Validation baseline: Python 3.10.18 in the yolo_anomalib environment.
GUI Framework | PyQt5 5.15.11 | The current implementation does not use PySide6.
AI Frameworks | Ultralytics YOLO11; Anomalib; PyTorch 2.4.1 validation environment | Runtime backend may use ONNX Runtime for deployed YOLO models.
Camera | Hikrobot MVS SDK | Industrial camera lifecycle, reconnect, exposure, and gain control.
Database | SQLite ? inspection_records.sqlite3 | Excel is a filtered export snapshot, not the searchable source of truth.
Packaging | PyInstaller one-folder Windows distribution | Hikrobot runtime and AI dependencies are bundled / preflight-checked.
Supported OS | Windows 10 / 11 for production station deployment | CI and some tools are platform-aware; camera production runtime is Windows-focused.
Workspace Contract | workspace.yaml | Defines training data, inference models, station data, Result, and release-artifact paths.
Repositories | yolo11_inference; Yolo11_auto_train; workspace integration repository | Child histories remain independent and are pinned by workspace commits.
Validation Status | Targeted automated regression recorded; physical line validation pending | Earlier runs: 381 passed / 2 skipped. Formal baseline: 45 passed; runs overlap.
Release Boundary | Formal software release ? production certification | Camera endurance, PLC, server sync, latency percentiles, and product accuracy remain separate gates.
Semantic Versioning Policy
MAJOR | Formal / incompatible application or workspace contract change.
MINOR | Backward-compatible operator, engineering, inspection, training, or deployment capability.
PATCH | Backward-compatible defect, reliability, packaging, or compatibility fix.

## Release Summary
Software Revision Note
Product Name : YOLO11 Integrated AI Inspection & Retraining System
Design Responsibility : DioWang
Prepared By : DioWang |  |  | Release Date : 2026 / 08 / 05
Date | Ver. | Subject | Description
12/19/2025 | v0.1.0 | Integrated Training and Inspection Foundation | Created the first end-to-end path from dataset preparation and YOLO training to camera inspection and saved results. Runtime checks included YOLO, Anomalib, component color, and expected position.
1/7/2026 | v0.1.1 | Security and Environment Stabilization | Restricted configuration, model, and image paths; standardized safe YAML loading, pinned dependencies, and the supported Python environment after early CI and test-environment failures.
1/15/2026 | v0.2.0 | DAG Automation and Quality-Control Tasks | Training steps became a dependency graph. Dataset lint, augmentation preview, batch inference, color / position QC, DVC synchronization, and environment diagnostics became explicit tasks.
2/11/2026 | v0.3.0 | Reproducible Experiments and Model Versioning | Training runs store parameters, metrics, and input hashes; unchanged data can skip retraining. ONNX / PT artifacts and the model version shown at the station can be traced to versioned files.
3/11/2026 | v0.3.1 | Architecture and CI Correctness Fixes | Replaced broad exception handling, corrected configuration / result contracts, fixed pytest crashes, and restored Ruff and strict MyPy checks without adding a new operator workflow.
3/30/2026 | v0.4.0 | Deployment Automation and Concurrent Inference | Camera capture, inference, UI updates, and result writes no longer share one blocking flow. Deployment / artifact commands and standalone-build checks were added.
3/31/2026 | v0.4.1 | Offline Packaging and Fusion Result Fixes | Fixed missing PatchCore assets in offline builds, incorrect Fusion result paths, and Anomalib heatmap threshold display in packaged applications.
5/28/2026 | v0.5.0 | Production Inspection and Edge Runtime | Missing and wrong-component decisions use configured slots instead of raw detection counts. PCBA preflight, editable model settings, failed-item evidence, edge-runtime checks, and Anomalib deployment were added.
6/11/2026 | v0.5.1 | Camera Runtime Stability Fixes | Made MVS shutdown idempotent, corrected DLL / config resolution, added camera-loss reconnect, removed a per-frame memory copy, and stopped workers from mutating shared model configuration.
6/25/2026 | v0.6.0 | Automated Station Operation | Auto Mode gained separate Arm / Start states, an operator phase banner, serial light control, and explicit confusion-matrix, false-reject, and missed-defect metrics. Color correction now runs before final OK / NG status.
6/30/2026 | v0.6.1 | Serial Light-Control Fixes | Stabilized COM-port light control and included pyserial in the packaged runtime so brightness control behaves the same in source and EXE execution.
7/9/2026 | v0.7.0 | Illumination Calibration and Inspection Traceability | Each model can store camera exposure, gain, and LED brightness. The calibration screen shows a live frame and convergence steps; inspection records include model, thresholds, timing, decision, and evidence paths.
7/13/2026 | v0.7.1 | Calibrated Auto-Inspection Startup Fix | Corrected Auto Mode startup after calibration so per-model camera / light values are active before automatic triggering begins.
7/24/2026 | v0.8.0 | Operator Review and Retraining Workflow | Added deterministic review processing, annotation repair, retraining-batch preparation, operator job controls, and the in-window training workspace. Result persistence was moved off the inspection loop.
7/30/2026 | v0.9.0 | Production Records and Deployment Gates | Added searchable SQLite inspection history, backup / restore, Excel snapshots, synchronization outbox, dataset conflict checks, position Golden Set / Gate, and matching ONNX / PT deployment contracts.
7/31/2026 | v0.10.0 | Acceptance and Atomic Inspection Releases | Model acceptance uses human-reviewed ground truth kept outside training data. YOLO, Anomalib, Fusion, and Stats Color references are activated as one inspection release; rollback restores the previous component set.
8/3/2026 | v0.11.0 | Unified Workspace and Station Data Migration | `workspace.yaml` defines training, model, station, result, and release-artifact paths. Migration tools move mutable data out of source trees and preserve access to existing evidence around Windows file locks.
8/5/2026 | v1.0.0 | First Formal Integrated Release | Declared the first stable application and workspace contract. GUI, package metadata, result services, and this revision note now use one authoritative system version. Field acceptance remains a separate production gate.

## Engineering Log
Engineering Development Log
Evidence source: Git history, current modules, tests, commands, and operating documents. Owner identifies the accountable release-document maintainer.
Recorded targeted runs: earlier suites reported 381 passed / 2 skipped; the v1.0.0 baseline suite reported 45 passed. Runs overlap. No full coverage report or physical production-line validation was performed.
Date | Version | Problem | Changes | Modules / Commands / Screens | Validation evidence | Known limitations | Commit evidence | Owner
12/19/2025 | v0.1.0 | Training utilities and inference code existed as separate scripts. There was no single path from prepared images to a saved inspection result, and configuration behavior differed between entry points. | Core changes - Built CLI and GUI entry points for dataset preparation, training, evaluation, and inference. - Connected Hikrobot capture to YOLO / Anomalib inference. - Added color, count, position, annotated-image, and result-persistence paths. | Training: src/picture_tool/main_pipeline.py, tasks/, train/yolo_trainer.py, gui/ Inference: core/detection_system.py, core/yolo_inference_model.py, core/anomalib_inference_model.py, camera/, app/gui/ Commands: picture-tool-pipeline, picture-tool-gui, yolo11-inference | Current regression (2026-08-05): tests/test_detection_system.py and training tests/test_pipeline_core_extended.py passed as part of the recorded 146-test and 107-test suites. | The recorded regression uses mocks / fixtures; it does not prove model accuracy, GPU throughput, or physical-camera stability. | Inference: 94327f3, 139850d Training: 006181d, cd63ca6 | Dio Wang
1/7/2026 | v0.1.1 | Early builds accepted paths outside intended project roots, dependency resolution varied by machine, and the test runner did not consistently match the supported Python environment. | Core changes - Added PathValidator and project-root allowlists. - Confirmed yaml.safe_load at configuration boundaries. Test / CI changes - Pinned runtime / development dependencies and aligned CI with the supported Python profile. - Fixed pytest-qt and temporary-directory test configuration. | core/security.py, core/config.py, main.py, requirements.txt, requirements-dev.txt, .github/workflows/, tests/conftest.py | Current regression: tests/test_security.py passed except one platform-specific symlink case. The supported yolo_anomalib environment imports torch successfully. | The default shell Python 3.11.4 still fails to initialize torch c10.dll; verification must use the documented Python 3.10 environment. | 0663847, 7be958f, 5ffe0f9, 0e613de, 11245d7 | Dio Wang
1/15/2026 | v0.2.0 | A linear task sequence reran unnecessary work and made dependency failures hard to locate. External paths and configuration files also crossed application boundaries without consistent rejection rules. | Core changes - Converted training tasks to a dependency-aware DAG with skip functions. - Added dataset_lint, aug_preview, batch_inference, qc_summary, color verification, position validation, and doctor tasks. Supporting changes - Added path traversal checks, safe YAML loading, pinned dependencies, and narrower exception handling. | Training: src/picture_tool/pipeline/core.py, tasks/quality.py, doctor.py, quality/dataset_linter.py Inference: core/security.py, core/config.py Commands: picture-tool-pipeline --tasks ..., picture-tool-doctor | Current regression: inference tests/test_security.py and training tests/test_dataset_readiness.py / test_tasks_integration.py passed. One Windows-only symlink security case was skipped. | DVC remote transfer and Docker deployment were not exercised in the 2026-08-05 run. Allowed roots still require deployment-specific configuration. | Inference: 0663847 Training: 672065c, a5e6752 | Dio Wang
2/11/2026 | v0.3.0 | Repeated training could not reliably determine whether input data changed. Runtime model files lacked a consistent identity, so station results could not be tied back to one training run. | Core changes - Stored experiment parameters, metrics, artifacts, and last_run_metadata.json. - Added content-hash skip logic and automatic ONNX export. Supporting changes - Added generated position configuration and versioned runtime model naming / display. | Training: tracking/experiment_tracker.py, utils/hashing.py, utils/onnx_exporter.py, position/position_config_gen.py Inference: core/services/model_version_registry.py, GUI status bar Artifacts: best.pt, best.onnx, last_run_metadata.json | Current regression: training tests/test_experiment_tracker.py and test_onnx_exporter_full.py passed in the 107-test suite. Model-version aliases are also checked by inference tests/test_system_version.py. | Hash equality proves input identity, not model quality. The recorded run did not connect to a remote MLflow server. | Inference: 165b23a, 9194581 Training release evidence: CHANGELOG v0.3.0 | Dio Wang
3/11/2026 | v0.3.1 | Architecture review found broad exception catches, inconsistent result / configuration contracts, crashing tests, and strict type-check failures that made CI results unreliable. | Core changes - Replaced generic exceptions with domain / infrastructure-specific handling. - Corrected result and configuration boundaries. Test / CI changes - Fixed pytest collection / teardown failures. - Restored Ruff and strict MyPy checks and synchronized documentation. | Training: src/picture_tool/exceptions.py, pipeline/, tracking/, tests/, CI workflows Inference: core/config.py, core/types.py, core/detection_system.py | Historical commits restored lint, type-check, and pytest gates. Current selected pipeline, experiment, and inference regressions pass; no separate field behavior changed. | This patch improves code correctness signals but does not measure inspection accuracy or runtime latency. | Inference: ab12ff0, 1551ba8 Training: ad55bb9, 1e079aa, 3d46099, bd17996, d102bb5 | Dio Wang
3/30/2026 | v0.4.0 | Camera acquisition, inference, rendering, and file writes could block each other. Rapid close / model-switch actions exposed worker lifecycle races, and copying trained artifacts into inference was manual. | Core changes - Split acquisition, inference, and storage into workers connected by bounded overwrite queues. - Added backpressure behavior, thread-safe shutdown, and async pipeline management. Supporting changes - Added deploy / artifact_bundle tasks, config export, preflight checks, and standalone build verification. | Inference: core/queues.py, core/workers.py, core/async_pipeline.py, app/gui/workers.py, build_exe.bat, verify_build.py Training: tasks/deploy.py, tasks/bundle.py Commands: picture-tool-pipeline --tasks deploy¦artifact_bundle | Current regression: tests/test_queues.py, test_workers.py, training test_runtime_pair_deployment.py, and pipeline tests passed. No continuous-load or latency percentile measurement was run. | Overwrite queues intentionally drop intermediate frames during sustained overload. No multi-hour camera / GPU soak result is recorded. | Inference: f9b9415, 53a949e, c92a2fe, ba89d16 Training: 8276a74 | Dio Wang
3/31/2026 | v0.4.1 | The standalone bundle could omit PatchCore runtime assets, and Fusion results used incorrect output paths / heatmap threshold presentation after packaging. | Core changes - Included offline PatchCore dependencies in the PyInstaller bundle. - Corrected Fusion result and heatmap save paths. Supporting changes - Corrected the Anomalib heatmap threshold shown to operators. | build_exe.bat, yolo11_inference.spec, core/anomalib_lightning_inference.py, core/fusion_inference.py, core/services/results/ | Formal-baseline regression on 2026-08-05: tests/test_fusion_inference.py and test_result_handler.py passed. | No fresh offline EXE was built during this documentation update; source-level regression does not prove installer completeness. | d2e3499, ca5ec10 | Dio Wang
5/28/2026 | v0.5.0 | Raw detection counts could not distinguish a missing slot from a wrong component. Model / result paths behaved differently after packaging, and pilot use lacked explicit startup and evidence checks. | Core changes - Added expected-slot, missing-item, wrong-slot, and position decision paths. - Added failed-component crops and model-config hot reload. Supporting changes - Added PCBA pilot preflight / acceptance reports, runtime diagnostics, and Anomalib training / deployment entry points. | Inference: core/services/missing_slot_checker.py, decision_engine.py, slot_roi.py, results/crops.py, app/gui/model_config_dialog.py, tools/pcba_pilot.py, tools/production_preflight.py Training command: picture-tool-anomalib | Current regression: tests/test_missing_slot_checker.py, test_decision_engine.py, test_production_preflight.py, and training test_model_acceptance_deployment.py passed. | PCBA1 A/B still require physical golden-board repeatability and known-NG validation. Small solder / surface defects remain outside YOLO slot logic. | Inference: 39d8e96, 30d9cf3, 9643558 Training: cda4ad3 | Dio Wang
6/11/2026 | v0.5.1 | Repeated shutdown could call the MVS SDK twice, camera loss was not recovered, DLL / model paths differed after packaging, and shared configuration was mutated during model switches. | Core changes - Made camera and image-writer shutdown idempotent. - Added camera-loss threshold and reconnect handling. - Corrected MVS DLL and project-root config resolution. - Replaced per-frame memcpy with a zero-copy view. - Stopped workers from mutating shared configuration. | camera/MVS_camera_control.py, camera/camera_controller.py, core/workers.py, core/services/results/image_queue.py, core/config.py, start.bat | Current regression: tests/test_mvs_camera_guards.py and worker / queue tests passed. | Physical cable / power-loss recovery and multi-hour capture stability were not measured. | c7d344d, e3a0883, c1500a0, 4e71f89, f875381, 56092c9, b09ffae | Dio Wang
6/25/2026 | v0.6.0 | Unattended inspection had no explicit arm / run state, operators could not see the active phase, lighting required manual adjustment, and review reports did not expose false-reject and missed-defect counts. | Core changes - Added separate Auto Arm and Start transitions plus an always-visible phase banner. - Added serial COM light on / off and brightness controls. - Added confusion matrix, false-reject rate, and missed-defect rate. - Applied color correction before the final inspection decision. | app/gui/auto_inspection_controller.py, app/gui/light_handler.py, core/services/light_controller.py, core/pipeline/steps.py, inspection metrics / result views Screens: Auto Mode banner, Lighting menu | Current regression includes detection-system tests; the 2026-08-05 formal-baseline run also passed light_controller, light_handler, and auto_inspection_controller_lifecycle tests. | Metrics require human-reviewed labels. PLC triggering and long-duration unattended operation are not recorded as field-validated. | 4e71f89, f875381, 56092c9, 8e54860, 41aa9ef, ac4e9d6, 9a5e100 | Dio Wang
6/30/2026 | v0.6.1 | Serial light control behaved differently after reconnection and pyserial was absent from some packaged runtimes. | Core changes - Stabilized COM-port selection and serial command handling. - Added pyserial to the packaged dependency set. | app/gui/light_handler.py, core/services/light_controller.py, requirements / PyInstaller configuration | Formal-baseline regression: 12 light_controller tests and 5 light_handler tests passed. | No physical light-controller model compatibility matrix or cable fault test is recorded. | 4f98e4b, 46c291c | Dio Wang
7/9/2026 | v0.7.0 | Fixed exposure and LED brightness caused color decisions to drift between products and stations. Operators could not see why auto-calibration converged or failed. | Core changes - Stored exposure, gain, brightness, and target luma in each model configuration. - Applied optical settings on model switch. - Added a live-preview calibration dialog, two-phase brightness search, per-step convergence log, and result status. - Expanded inspection snapshots with config and decision evidence. | core/services/auto_calibrator.py, calibration_session.py, app/gui/calibration_dialog.py, calibration_handler.py, camera/camera_controller.py, models/*/*/*/config.yaml Screen: Lighting > Illumination Calibration | Current regression: tests/test_auto_calibrator.py, test_calibration_session.py, and test_calibration_handler.py passed. | No cross-camera / cross-light repeatability study is recorded. Calibration optimizes image brightness; it does not by itself prove color-class accuracy. | d941094, 50924ad, 92b99e2, 3b015e6, 3224ecf, 55b70d1 | Dio Wang
7/13/2026 | v0.7.1 | After calibration, Auto Mode could start before the selected model's exposure / gain / brightness values were applied consistently. | Core changes - Ordered calibrated optical-setting application before automatic inspection startup. Supporting changes - Kept the light keepalive state synchronized with the calibration result. | app/gui/auto_inspection_controller.py, app/gui/light_handler.py, core/services/calibration_session.py | Formal-baseline regression: tests/test_auto_inspection_controller_lifecycle.py passed; calibration session / handler tests also passed in the earlier targeted run. | The tests simulate controller state; an actual camera-light startup timing test is not recorded. | a7274b7 | Dio Wang
7/24/2026 | v0.8.0 | Reviewed false rejects / misses were not processed deterministically, annotation repair was not auditable, and retraining required manual cross-project handoff. | Core changes - Added deterministic review classification and repair history. - Added guarded retraining preparation and portable operator job control. - Added review, processing, and training workspaces to the inference GUI. Supporting changes - Moved result persistence off the inspection loop and fixed saved / displayed artifact synchronization. | Inference: tools/review_*, app/gui/review_cases_dialog.py, processing_batch_dialog.py, retraining_workspace_host.py, core/services/results/ Training: operator_job.py, gui/operator_workflow_panel.py | Current regression: review_workflow and training operator / dataset tests passed. Formal-baseline result-handler and lifecycle tests also passed. | This release created the workflow but did not yet provide the complete searchable SQLite history and release-level acceptance introduced in later minors. | Inference: 0f2750b, 663f2dd, c9ab6fa, 0d3512d, 36a8a90, 1e4d637 Training: 7eff716, ab2e4c6, 9969971, ae6c5c7 | Dio Wang
7/30/2026 | v0.9.0 | False rejects and missed detections were saved but not routed into a controlled correction / retraining path. Excel-only history was difficult to query, and deployment could pair an ONNX file with the wrong PT checkpoint. | Core changes - Added review, annotation repair, batch preparation, and operator training screens. - Added stable sample IDs, dataset conflict checks, family-aware split checks, position Golden Set / Gate, and matching ONNX-PT deployment contracts. - Moved persistence off the inspection critical path. Supporting changes - Added SQLite inspections, ai_predictions, inspection_artifacts, review_events, maintenance_events, and inspection_sync_outbox tables. | Inference: app/gui/review_cases_dialog.py, training_batch_dialog.py, inspection_history_page.py; core/services/inspection_database.py, inspection_sync.py; tools/review_* Training: operator_acceptance.py, operator_job.py, runtime_pair_deployment.py, position/position_gate.py | Current regression: review_workflow, inspection_database, inspection_sync, operator_acceptance, operator_dataset_conflicts, position_gate, runtime_pair_deployment, and full_pipeline_dryrun tests passed. | The company-server API was not exercised. Cable1/A has no confirmed true color-NG set, so color escape rate remains UNKNOWN. | Inference: bf5676d, 0f2750b, 0852398 Training: 054aa6f, ab2e4c6, cf0a9c6 | Dio Wang
7/31/2026 | v0.10.0 | Switching YOLO, Anomalib, or color rules independently could create an untested production combination. Acceptance samples could also be contaminated by training use, and rollback scope was unclear. | Core changes - Added model-acceptance UI / headless runner using human-reviewed ground truth stored outside training data. - Added version records for model and Stats Color components. - Added DRAFT -> TESTED -> activation flow and an active-release pointer. - Rollback restores the previous release pointer and all component references in that release. | app/acceptance/, app/gui/inspection_version_workspace.py, inspection_releases_dialog.py core/services/model_acceptance.py, acceptance_matrix.py, inspection_component_catalog.py, inspection_release_store.py, color_baseline_recalibration.py Command: start_model_acceptance.bat | Current regression: tests/test_model_acceptance.py and test_inspection_release.py passed in the 146-test suite. | Rollback does not revert the application EXE, database schema, or inspection history. Acceptance quality still depends on correct human-reviewed labels and representative samples. | Inference: 30719cb Training: dd5ff30 Workspace: 3960f9f | Dio Wang
8/3/2026 | v0.11.0 | Source code, station configuration, inspection evidence, and trained artifacts were mixed in repository-relative folders. Launching from a different directory or moving a station could resolve paths incorrectly; open Windows files blocked simple moves. | Core changes - Added workspace.yaml as the cross-project path contract. - Added station-data and result relocation tools with legacy-path compatibility and lock-aware copying / verification. Supporting changes - Separated station_data, Result, release_artifacts, source, and model ownership. - Kept training and inference as independent repositories pinned by workspace commits. | workspace.yaml, README.md Inference: core/workspace.py, core/station_data.py, tools/migrate_station_data.py, tools/relocate_result_data.py Training: workspace_paths.py, scripts/migrate_workspace_paths.py Commands: start_inference.bat, start_training.bat | Current regression: both projects' test_workspace_paths.py and inference test_relocate_result_data.py passed. | Migration is local-station tooling, not a distributed transaction. Backups and process shutdown are still required before production relocation. | Inference: b5fe570, 8722edc, 2ad419c Workspace: 9fefd7a, 6e35676, 5ac8296 | Dio Wang
8/5/2026 | v1.0.0 | The integrated application still reported a pre-release 0.x version and lacked one formal baseline tying GUI display, package metadata, result services, release history, and validation evidence together. | Core changes - Set core._version.__version__ to 1.0.0 as the authoritative application version. - Declared the integrated training, inference, acceptance, and workspace contracts as the first formal software baseline. Supporting changes - Kept GUI status / About, package metadata, and result-service exports on that value. - Split documentation into Release Summary, Engineering Log, and Validation Evidence. | core/_version.py, core/__init__.py, core/services/results/__init__.py, pyproject.toml, app/gui/main_window.py, docs/yolo_inference_RevisionNote.xlsx | Formal-baseline run: 45 passed across system_version, Fusion, result handling, light control, Auto Mode lifecycle, and runtime manifest. Earlier targeted runs recorded 381 passed and 2 skipped; runs overlap and are not a coverage report. | Formal software release is not production-line certification. Physical camera endurance, PLC integration, server synchronization, latency percentiles, and product-specific accuracy acceptance remain separate gates. Git tag / release package is not created by this document update. | Working tree baseline dated 2026-08-05; publish commit and Git tag v1.0.0 still pending. | Dio Wang

## Validation Evidence
Validation Evidence ? 2026-08-05
Targeted regression only. Full commands are retained as comments on the Runner cells; results are not a field-acceptance certificate.
Date | Project | Python | Torch | Environment | Runner | Scope | Status | Count | Notes
2026-08-05 | yolo11_inference | 3.10.18 | 2.4.1 | yolo_anomalib | pytest | Detection; queues; workers; camera guards; calibration; review; SQLite; releases; acceptance; workspace; relocation | PASS | 146 passed | Targeted regression; not the complete suite. Warning reported by the mocked image writer after test completion.
2026-08-05 | Yolo11_auto_train | 3.10.18 | 2.4.1 | yolo_anomalib | pytest | Training pipeline; experiments; ONNX export; runtime pairing; operator acceptance; dataset conflicts; position; workspace | PASS | 107 passed | Targeted regression; not a coverage measurement.
2026-08-05 | yolo11_inference | 3.10.18 | 2.4.1 | yolo_anomalib | pytest | Security; runtime preflight; slot decisions; inspection sync; calibration; production preflight; system version | PASS | 84 passed, 1 skipped | Skipped case is platform-specific. No camera, PLC, server, or GPU load test.
2026-08-05 | Yolo11_auto_train | 3.10.18 | 2.4.1 | yolo_anomalib | pytest | Dataset readiness; task integration; deployment; position; color thresholds; full-pipeline dry run | PASS | 44 passed, 1 skipped | Dry-run and unit/integration coverage only; no full model training was executed.
2026-08-05 | yolo11_inference | 3.11.4 | Import failed | Default shell | pytest | Collection bootstrap | BLOCKED | collection error | torch c10.dll failed to initialize. Use D:/miniconda/envs/yolo_anomalib/python.exe for project verification.
Not recorded | Integrated system | N/A | N/A | Production station | Field validation | Physical camera; PLC; production server; latency; model accuracy | NOT RECORDED |  | Do not infer field reliability, latency percentiles, or inspection accuracy from the automated tests above.
2026-08-05 | v1.0.0 formal baseline | 3.10.18 | 2.4.1 | yolo_anomalib | pytest | System version; Fusion; result persistence; lighting; Auto Mode; runtime manifest | PASS | 45 passed | Overlaps the earlier system_version run. Warning from the mocked image writer was emitted after successful test completion. No EXE build or field test.
Note on F5: Exact recorded command / activity: python -m pytest test_detection_system test_queues test_workers test_mvs_camera_guards test_calibration_session test_review_workflow test_inspection_database test_inspection_release test_model_acceptance test_workspace_paths test_relocate_result_data
Note on F6: Exact recorded command / activity: python -m pytest test_pipeline_core_extended test_experiment_tracker test_onnx_exporter_full test_runtime_pair_deployment test_operator_acceptance test_operator_dataset_conflicts test_position_gate test_workspace_paths
Note on F7: Exact recorded command / activity: python -m pytest test_security test_runtime_preflight test_missing_slot_checker test_decision_engine test_inspection_sync test_auto_calibrator test_calibration_handler test_production_preflight test_system_version
Note on F8: Exact recorded command / activity: python -m pytest test_dataset_readiness test_tasks_integration test_model_acceptance_deployment test_position_deployment test_threshold_calibration test_full_pipeline_dryrun
Note on F9: Exact recorded command / activity: python -m pytest <targeted suite>
Note on F10: Exact recorded command / activity: Continuous capture / camera reconnect / PLC trigger / server sync / measured model acceptance
Note on F11: Exact recorded command / activity: python -m pytest test_system_version test_fusion_inference test_result_handler test_light_controller test_light_handler test_auto_inspection_controller_lifecycle test_runtime_manifest